## ProjectTaskList
LIGHTNING TRIGGER
[7 empty] | Budget | Est. Hours | Act. Hours |  | Task List Templates
|  | Project Start | 2017-01-01 |  |  | Totals | 2000 | 0 | 0 |  | © 2017 Vertex42 LLC
TASK | OWNER | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
HARDWARE | [5 empty] | 0
Draw Prototype Schematic |  | HIGH |  |  | 100% | 1
Layout Prototype PCB |  | HIGH |  |  | 100% | 1
Assemble Prototype PCB |  | HIGH |  |  | 100% | 1
Rework Prototype Schematic |  | LOW |  |  | 20% | 0
Rework Prototype PCB |  | LOW |  |  | 0% | 0
Assemble Rework Prototype PCB |  | LOW |  |  | 0% | 0
Design encloosure box cutouts |  | LOW |  |  | 0% | 0
0
SOFTWARE | [5 empty] | 0
Develop Arduino prototype software |  | MEDIUM |  |  | 0% | 0
Triggering algorithm |  |  |  |  | 95% | 0
Menu structure |  |  |  |  | 90% | 0
Sound Visualiser |  |  |  |  | 0% | 0
Calibration |  |  |  |  | 60% | 0
Develop Android Application |  | LOW |  |  | 5% | 0
0
Port software off Arduino (To Atmel Studio) |  | LOW |  |  | 0% | 0
TESTING | [5 empty] | 0
Design testing jig |  | LOW |  |  | 0% | 0
Design software testing |  | LOW |  |  | 0% | 0
0
0
CERTIFICATIION | [5 empty] | 0
FCC Certification |  | LOW |  |  | 0% | 0 | 2000
CE Certification |  | LOW |  |  | 0% | 0
UL Certification |  | LOW |  |  | 0% | 0
0
0
0
0
0
0
0

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/task-list-template.html
About
This task list template provides a simple way to list and track your tasks. It also includes columns for budget and hours. You can delete or add columns and rows as needed. This worksheet was kept simple intentionally. If you would a more advanced way to create a task list for a project, try a Gantt Chart.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
Conditional Formatting
The Priority, % Complete, and Done columns use conditional formatting in different ways. If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
The Done column is updated automatically. When you enter 100% in the % Complete column, the checkmark should appear in the Done column. You can use the drop-down in the Done column if you prefer.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.